## Initial Plan
Color Coding |  |  | Completed |  |  |  | SPRING 2022 SEMESTER
In Progress
[6 empty] | Week # | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
[6 empty] | Date | 2022-01-25 | 2022-02-08 | 2022-02-15 | 2022-02-22 | 2022-03-01 | 2022-03-08 | 2022-03-22 | 2022-03-29 | 2022-04-05 | 2022-04-12 | 2022-04-19 | 2022-04-26 | 2022-05-03 | 2022-05-10 | 2018-05-08
Project Phase | Activity |  | Task Owner Name | Start Date | End Date | Progress %
Project Initiation | Discuss project proposals |  | ALL | 2022-01-25 | 2018-01-27 | 100%
| Confirm Project Team Roles |  | ALL | 2022-01-25 | 2018-01-27 | 100%
| Develop two business cases |  | Kaneshk K Sonee | 2018-01-27 | 2022-02-08 | 100%
| Develop Project Initiation Document (PID) |  | Kaneshk K Sonee | 2018-02-08 | 2022-02-15 | 100%
| Produce initial Project Plan, RACI |  | Kaneshk K Sonee, Neerav Poriya | 2022-02-15 | 2022-02-22 | 100%
MILESTONE 1: INITIAL PROJECT PLAN COMPLETED
Requirements Definition | Produce BRM diagram, define User Roles |  | Limisha Oliveira | 2022-02-22 | 2022-03-01 | 100%
| Produce Context Diagram, Define System Interfaces |  | Sayali Tandel | 2022-02-22 | 2022-03-01 | 100%
| Define Business Requirements |  | Sayali Tandel | 2022-02-22 | 2022-03-01 | 100%
| Agree to System Requirements types |  | All | 2022-03-01 | 2022-03-08 | 100%
| Define Functional Decomposition |  | All | 2022-03-01 | 2022-03-08 | 100%
| Produce RCT document |  | Sayali Tandel | 2022-03-08 | 2022-03-22 | 100%
| Decide which features to implement this semester |  | All | 2022-03-08 | 2022-03-22 | 100%
| Produce analysis diagrams (UML, DFD) |  | Sayali Tandel | 2022-03-22 | 2022-04-05 | 100%
| Define functional requirements (User Stories) |  | Sayali Tandel | 2022-03-22 | 2022-04-05 | 100%
| Update Project Plan with additional requirements tasks |  | Kaneshk K Sonee | 2022-03-22 | 2022-04-05 | 100%
MILESTONE 2: REQUIREMENTS COMPLETED
Design | Architecture design (2 diagrams) |  | Neerav Poriya | 2022-04-05 | 2022-04-12 | 100%
| Database Design (ERD, Table spec) |  | Neerav Poriya | 2022-04-05 | 2022-04-12 | 100%
| Establish Github Project |  | Neerav Poriya | 2022-04-05 | 2022-04-12 | 100%
| Class Diagram (UML) |  | Limisha Oliveira | 2022-04-05 | 2022-04-12 | 100%
| Sequence Diagram (UML) |  | Sayali Tandel | 2022-04-05 | 2022-04-12 | 100%
| Populate test data in the database tables |  | Neerav Poriya | 2022-04-06 | 2022-04-13 | 100%
| Source code in GitHub repository, executable code ready for testing |  | Neerav Poriya | 2022-04-07 | 2022-04-14 | 100%
MILESTONE 3: DESIGN COMPLETED
Code | Account Management | GUI and Functionality Detailed Design
|  | Creating User Login Page | Neerav Poriya | 2022-04-05 | 2022-04-19 | 100%
|  | Creating User Registration Page | Neha Chudekar | 2022-04-05 | 2022-04-19 | 100%
|  | Creating User Profile Page | Limisha Oliveira | 2022-04-05 | 2022-04-19 | 100%
|  | Establish code repository in GitHUb | Tushar Varma | 2022-04-05 | 2022-04-19 | 100%
|  | Coding & Implemenation | Tushar Varma | 2022-04-05 | 2022-04-19 | 75%
Feature Breakdown
01.01 Creating a user account
|  | Sign-up page for Customers | Neerav Poriya | 2022-04-12 | 2022-04-19 | 100%
01.03 Use Account Authentication
|  | Validate login for Customers | Neerav Poriya | 2022-04-12 | 2022-04-19 | 75%
MILESTONE 4: CODING COMPLETED
Integration & Testing |  | Plan testing, produce a Test Plan document | Chandini reddy | 2022-04-19 | 2022-04-26 | 100%
|  | Evaluate Features to be Tested | Neha Chudekar | 2022-04-19 | 2022-04-26 | 100%
|  | Design Test Cases | Chandini reddy | 2022-04-19 | 2022-04-26 | 100%
|  | Execute Test Cases | Chandini reddy | 2022-04-19 | 2022-04-26 | 75%
|  | Anaylze Test Results | Neha Chudekar | 2022-04-19 | 2022-04-26 | 75%
MILESTONE 5: TESTING COMPLETED
Project Presentation | Prepare Application Demo for the Presentation |  | ALL | 2022-05-03 | 2018-05-10 | 0%