## Road Map
Flaunt
|  |  | Release 1 |  | Release 2
Application Modules | Feature Backlog | Story Points |  |  | Iteration 3 - 11/18/22 | Iteration 4 - 12/16/22
Module 1 - Account management | 01.01 Creating a User account
| 01.02 Modify user account details | 3 |  |  |  | x
01.03 User account Authentication
| 01.04 View Account information | 2 |  | x
| 01.05 Deleting a user | 2 |  | x
| 01.06 Utilizing Customer Support(FAQs & Email only) | 3 | x
Module 2 - Browse Product | 02.01 Use Navigation Bar | 3 | x
| 02.02 View Featured Products | 4 |  | x
| 02.03 View Partnered Brands | 3 | x
| 02.04 Sign in to User Account | 3 |  | x
02.05 Use Seach Bar
| 02.06 Add products to shopping cart (wishlist) | 4 |  |  | x
| 02.07 view Footer section (aboutus, contactus, Teams) | 3 | x
Module 3 - Purchase Management | 03.01 View/ Edit shopping Cart | 4 |  |  |  | x
03.02 Use Product Checkout
03.03 Applying Coupons
| 03.04 Submit Order | 2 |  |  |  | x
Module 4 - Payment Gateway | 04.01 Defining Payment Mode | 3 |  |  | x
04.02 Payment Validation (by 3rd party vendor)
Module 5 - Logistics service provider | 0.5.01 Delivery Tracking for the customer (by using 3rd party vendor)
05.02 Tracking Products for returned orders (by using 3rd party vendors)
Module 6 - Advertising Media | 06.01 Getting a coupon/ discount based on purchase
| 06.02 View banner ads on homepage | 3 |  |  |  | x
|  | VELOCITY: | 12 | 11 | 7 | 12

## Story Map
Epics |  | Flight Reservation System (Travelo) - User Story Map
Epic 1 - Account Management |  | Epic 1 - Account Management | Epic 2 - Browse Products | Epic 3 - Purchase Management | Epic 4 - Payment gateway | Epic 5 - logistics service provider | Epic 6 - Advertising media
Epic 2 - Browse Products | User Stories | 01.06 Utilizing Customer Support(FAQs & Email only) | 02.01 Use Navigation Bar
Epic 3 - Purchase Management |  |  | 02.03 View Partnered Brands
Epic 4 - Payment gateway |  |  | 02.07 view Footer section (aboutus, contactus, Teams) |  |  |  |  | Iteration 1
Epic 5 - logistics service provider
Epic 6 - Advertising media |  | 01.04 View Account information | 02.02 View Featured Products
|  | 01.05 Deleting a user | 02.04 Sign in to User Account |  |  |  |  | Iteration 2
|  |  | 02.06 Add products to shopping cart (wishlist) |  | 04.01 Defining Payment Mode
Iteration 3
|  | 01.02 Modify user account details |  | 03.01 View/ Edit shopping Cart
03.04 Submit Order
[7 empty] | 06.02 View banner ads on homepage | Iteration 4