## I4
Task # | Iteration | Module Name | RCT.ID | Core Feature | Task Description | Start Date | End Date | Status | Task Owner
1 | R2 I4 | Account Details | 1.02 | Modify User account | Core Functionality | 11-25-22 | 2022-03-12 | 100% | Tushar Varma
2 | R2 I4 | Account Details | 1.02 | Modify User account | GUI Features | 11-25-22 | 2022-03-12 | 100% | Neha Chudekar
3 | R2 I4 | Account Details | 1.02 | Modify User account | DF-In - Data Flow In | 11-25-22 | 2022-03-12 | 100% | Neerav Poriya
4 | R2 I4 | Account Details | 1.02 | Modify User account | DF-out - Data Flow Out | 11-25-22 | 2022-03-12 | 100% | Neerav Poriya
5 | R2 I4 | Account Details | 1.02 | Modify User account | Test If user is able to modify the details | 11-26-22 | 2022-03-12 | 100% | Tushar Varma
6 | R2 I4 | Purchase Management | 3.01 | View/Edit Shopping Cart | Core Functionality | 11-27-22 | 2022-06-12 | 100% | Neha Chudekar
7 | R2 I4 | Purchase Management | 3.01 | View/Edit Shopping Cart | GUI Features | 11-27-22 | 2022-06-12 | 100% | Neerav Poriya
8 | R2 I4 | Purchase Management | 3.01 | View/Edit Shopping Cart | DF-In - Data Flow In | 11-27-22 | 2022-06-12 | 100% | Neerav Poriya
9 | R2 I4 | Purchase Management | 3.01 | View/Edit Shopping Cart | DF-out - Data Flow Out | 11-27-22 | 2022-06-12 | 100% | Tushar Varma
10 | R2 I4 | Purchase Management | 3.01 | View/Edit Shopping Cart | Test if the shopping cart is visible | 11-29-22 | 2022-06-12 | 100% | Tushar Varma
11 | R2 I4 | Purchase Management | 3.01 | View/Edit Shopping Cart | Test if the shopping cart is editable | 11-29-22 | 2022-06-12 | 100% | Tushar Varma
12 | R2 I4 | Purchase Management | 3.04 | Submit order | Core Functionality | 11-30-22 | 2022-10-12 | 100% | Neerav Poriya
13 | R2 I4 | Purchase Management | 3.04 | Submit order | GUI Features | 2022-02-12 | 2022-10-12 | 100% | Neerav Poriya
14 | R2 I4 | Purchase Management | 3.04 | Submit order | DF-In - Data Flow In | 11-30-22 | 2022-10-12 | 100% | Neerav Poriya
15 | R2 I4 | Purchase Management | 3.04 | Submit order | DF-out - Data Flow Out | 11-30-22 | 2022-10-12 | 100% | Neerav Poriya
16 | R2 I4 | Purchase Management | 3.04 | Submit order | Test if the order is confirmed | 2022-04-12 | 2022-10-12 | 100% | Neha Chudekar
17 | R2 I4 | Advertising Media | 6.02 | View Banner Ads Homepage | Core Functionality | 2022-05-12 | 12-16-22 | 100% | Neha Chudekar
18 | R2 I4 | Advertising Media | 6.02 | View Banner Ads Homepage | GUI Features | 2022-08-12 | 12-16-22 | 100% | Neha Chudekar
19 | R2 I4 | Advertising Media | 6.02 | View Banner Ads Homepage | Test if banner ads are visible | 2022-10-12 | 12-16-22 | 100% | Neha Chudekar
20 | R2 I4 | Advertising Media | 6.02 | View Banner Ads Homepage | Test if incase of internet loss is the banner visible | 2022-12-12 | 12-16-22 | 100% | Neerav Poriya